## Revision
Revision History
Version | Date | Revision Content | Created by
W1 | 2023-05-12 | Weekly report for W1 (8-May -> 12-May) | Duy Tran
W2 | 2023-05-18 | Weekly report for W2 (15-May -> 19-May) | Duy Tran
W3 | 2023-05-26 | Weekly report for W2 (22-May -> 26-May) | Duy Tran
W4 | 2023-06-02 | Weekly report for W4 (29-May -> 2-Jun) | Duy Tran
W5 | 2023-06-09 | Weekly report for W5 (5-Jun -> 9-Jun) | Duy Tran

## W1
1. Information
|  | Duration: | From | 2023-05-08 | To | 2023-05-12
|  | Status: | Open | Normal | Delay | Pending | Done
|  | Assignment: | Thien Pham | Duy Tran | Khoi Nguyen | All members | RVC
2. Risks
| No. | Risks | Description | Scope | Action Description | Status
3. Progress
| No. | Tasks | Start date | End date | Assignment | Progress(%) | Status | Issue/Q&A | Cause/Solution | Remark
| 1 | Understanding S4, update sharing document for CAN_ETH_conversion module. Need a clear list of QnA. | 2023-04-20 | 2023-05-19 | Thien Pham | N/A | Normal
| 2 | Translate 4 files | 2023-04-27 | 2023-05-12 | Thien Pham | 100 | Done
| 3 | Running Sample app for CAN_ETH_conversion module | 2023-05-05 | 2023-05-16 | Thien Pham | 10 | Normal
| 4 | Understanding S4, update sharing document for CAN Routing module. Need a clear list of QnA. | 2023-04-20 | 2023-05-19 | Khoi Nguyen | N/A | Normal
| 5 | Translate 4 files | 2023-04-27 | 2023-05-12 | Khoi Nguyen | 100 | Done
| 6 | Running Sample app for CAN Routing module | 2023-05-05 | 2023-05-16 | Khoi Nguyen | 10 | Normal
| 7 | Understanding S4, update sharing document for EthernetSwitchControl module. Need a clear list of QnA. | 2023-04-20 | 2023-05-19 | Duy Tran | N/A | Normal
| 8 | Translate 4 files | 2023-04-27 | 2023-05-12 | Duy Tran | 100 | Done
| 9 | Running Sample app for EthernetSwitchControl module | 2023-05-05 | 2023-05-16 | Duy Tran | 50 | Normal
4. Next plan:
| No. | Action Items | Assignment
| 1 | Run SampleApp for Gateway (Task 2) and create a guideline | All members
2
3
4

## W2
1. Information
|  | Duration: | From | 2023-05-15 | To | 2023-05-19
|  | Status: | Open | Normal | Delay | Pending | Done
|  | Assignment: | Thien Pham | Duy Tran | Khoi Nguyen | All members | RVC
2. Risks
| No. | Risks | Description | Scope | Action Description | Status
|  | Execution SampleApp for CANrout module | Because of lacks of env: SW: PCAN View HW: PCAN FD => Cause delay for this task. | Khoi Nguyen | Try to execuse with workaround solution
3. Progress
| No. | Tasks | Start date | End date | Assignment | Progress(%) | Status | Issue/Q&A | Cause/Solution | Remark
| 1 | Understanding S4, update sharing document for CAN_ETH_conversion module. | 2023-05-18 | 2023-05-19 | Thien Pham | 70 | Normal | Will have a short list of questions.
| 2 | Update sharing document regarding to how-to run SampleApp for CanEthConv | 2023-05-15 | 2023-05-19 | Thien Pham | 100 | Done
| 3 | Running Sample app for CAN_ETH_conversion module | 2023-05-15 | 2023-05-19 | Thien Pham | 100 | Done
| 4 | Translate R-CarS4_Gateway_SampleProgramTestReport_CanEthConv.xlsx | 2023-05-18 | 2023-05-23 | Thien Pham | 0 | Open
| 5 | Update the Introduction Slides (for Can Routing Module) | 2023-05-15 | 2023-05-19 | Khoi Nguyen | 100 | Done
| 6 | Running Sample app for CAN Routing module | 2023-05-15 | 2023-05-19 | Khoi Nguyen | 50 | Pending | Need HW & SW to run sample app: SW: PCAN driver (PCAN -view, PCANBasic API) HW: PCAN-USB x6, PCAN-USB Pro FD | Try to execuse with workaround solution
| 7 | Translate R-CarS4_Gateway_SampleProgramTestReport_CanRout.xlsx | 2023-05-17 | 2023-05-17 | Khoi Nguyen | 100 | Done
| 8 | Execuse Sample Application for Ethernet Switch Control Module: - Hardware set-up. - Execuse all Test Cases. - Make the Sample App Guideline. | 2023-05-05 | 2023-05-16 | Duy Tran | 100 | Done
| 9 | Update the Introduction Slides (for Ethernet Switch Control Module) | 2023-05-15 | 2023-05-19 | Duy Tran | 100 | Done
| 10 | Translate R-CarS4_Gateway_SampleProgramTestReport_EthSwtCont.xlsx | 2023-05-17 | 2023-05-17 | Duy Tran | 100 | Done
4. Next plan:
| No. | Action Items | Assignment
1
2
3
4

## W3
1. Information
|  | Duration: | From | 2023-05-22 | To | 2023-05-26
|  | Status: | Open | Normal | Delay | Pending | Done
|  | Assignment: | Thien Pham | Duy Tran | Khoi Nguyen | All members | RVC
2. Risks
| No. | Risks | Description | Scope | Action Description | Status
3. Progress
| No. | Tasks | Start date | End date | Assignment | Progress(%) | Status | Issue/Q&A | Cause/Solution | Remark
| 1 | Exceution of SampleApp Testcases (53/53 CanEthConv and 67/67 CanEthConv PackLib) | 2023-05-18 | 2023-05-19 | Thien Pham | 85 | Normal |  |  | - All basic tests done, test reported done. - For performance test we don't know how to execute - Already report the case to Toan Pham, wait feedback so that we can continue work on performance testing.
| 2 | Update sharing document regarding to how-to run SampleApp for CanEthConv | 2023-05-22 | 2023-05-26 | Thien Pham | 100 | Done
| 3 | DUT for - R_CanEthConv_Init - CreateEthHeaderIpv4Ntscf | 2023-05-22 | 2023-05-26 | Thien Pham | 20 | Normal |  |  | - Understand the TableDriven workflow - Need more time to study the details - Created first 4 testcases
| 4 | Running Sample app for CAN Routing module | 2023-05-15 | 2023-05-19 | Khoi Nguyen | 50 | Pending
| 5 | Refer SIVI project for testing sample app by CANoe | 2023-05-22 | 2023-05-26 | Khoi Nguyen | 60 | Normal
| 6 | Execute Sample App (6/7 Test Cases) of Ethernet Switch Control Module and Get Test Log, Make Test Report. | 2023-05-22 | 2023-05-23 | Duy Tran | 95 | Done |  |  | Can mark as Done because 1 Test Case needs Linux PC to boot CA55 core.
| 7 | Investigate DUT (Driver Unit Test) process: - Set up Cantata environment. - How to make Test Specification & create Test Application. - How to run Test Application in QAsystem Cantata. - Execute 2 functions of EthSwtCont module (SetMacTbl, CheckMacTblCfg) | 2023-05-23 | 2023-05-26 | Duy Tran | 25 | Normal
4. Next plan:
| No. | Action Items | Assignment
1
2
3
4

## W4
1. Information
|  | Duration: | From | 2023-05-29 | To | 2023-06-02
|  | Status: | Open | Normal | Delay | Pending | Done
|  | Assignment: | Thien Pham | Duy Tran | Khoi Nguyen | All members | RVC
2. Risks
| No. | Risks | Description | Scope | Action Description | Status
3. Progress
| No. | Tasks | Start date | End date | Assignment | Progress(%) | Status | Issue/Q&A | Cause/Solution | Remark
| 1 | DUT for - Function 1 - R_CanEthConv_Init - Setup Environment - Study Table Driven Script - Study Cantata Environment - Generate Test App - Execute 12 testcases, expect all PASSED | 2023-05-29 | 2023-06-02 | Thien Pham | 100 | Done |  |  | ETA: 4MD in the trial phase.
| 2 | DUT for - Function 2 - CreateEthHeaderIpv4Ntscf - Study Table Driven Script - Generate Test App - Execute TBD testcases, expect all PASSED | 2023-06-05 | 2023-06-09 | Thien Pham | 0 | Open |  |  | Seems a complecated function
| 3 | Running Sample app for CAN Routing module | 2023-05-15 | 2023-06-01 | Khoi Nguyen | 50 | Pending
| 4 | Catch message from board to CANoe based on RCAR_S4_SPRINT14_CAN_DEVELOP project | 31/5/2023 | 2023-06-01 | Khoi Nguyen | 30 | Normal |  |  | Detected: . CANoe can send . CAN/LIN board has tranceiver .
| 5 | Refer SIVI project for testing sample app by CANoe | 2023-05-22 | 2023-06-01 | Khoi Nguyen | 80 | Normal
| 6 | Investigate DUT (Driver Unit Test) process: - Set up Cantata environment. - How to make Test Specification & create Test Application. - How to run Test Application in QAsystem Cantata. - Execute 2 functions of EthSwtCont module (SetMacTbl, CheckMacTblCfg) (Request by REL) - Make test report | 2023-05-29 | 2023-05-31 | Duy Tran | 100 | Done
| 7 | Self-investigate DUT for complex function (SetL2L3UpRuleTbl) | 2023-06-01 | 2023-06-02 | Duy Tran | 100 | Done
4. Next plan:
| No. | Action Items | Assignment
1
2
3
4

## W5
1. Information
|  | Duration: | From | 2023-06-05 | To | 2023-06-09
|  | Status: | Open | Normal | Delay | Pending | Done
|  | Assignment: | Thien Pham | Duy Tran | Khoi Nguyen | All members | RVC
2. Risks
| No. | Risks | Description | Scope | Action Description | Status
3. Progress
| No. | Tasks | Start date | End date | Assignment | Progress(%) | Status | Issue/Q&A | Cause/Solution | Remark
| 1 | Research and execute all DUT for CreateEthHeaderIpv4Ntscf | 2023-06-03 | 2023-06-08 | Thien Pham | 100% | Normal |  |  | If I have time, I will study some more cases for DUT.
| 2 | Create DUT_Notes_During_Trial report | 2023-06-09 | 2023-06-09 | Thien Pham | 100% | Normal
| 3 | Running Sample app for CAN Routing module | 2023-05-15 | 2023-06-09 | Khoi Nguyen | 50 | Pending
| 4 | Catch message from board to CANoe based on RCAR_S4_SPRINT14_CAN_DEVELOP project | 5/42/2023 | 2023-06-09 | Khoi Nguyen | 50 | Normal |  |  | Can't send/receive CAN message cause of B0-2nd CPU It's take a little time to compare B0-1st CPU and B0-2nd CPU
| 5 | Compare B0-1st CPU and B0-2nd CPU | 2023-06-08 | 2023-06-09 | Khoi Nguyen | 30 | Normal
| 6 | Research and Implementation of new methods to make DUT report: - Create a report successfully. - Create a guideline. | 2023-06-05 | 2023-06-06 | Duy Tran | 100 | Done
| 7 | Research and Know How to execuse Integration Test. | 2023-06-07 | T.B.D | Duy Tran | 20 | Normal
4. Next plan:
| No. | Action Items | Assignment
1
2
3
4