## Sheet1
1. Information
|  | Duration: | From | 2023-06-12 | To | 2023-06-16
|  | Status: | Open | Normal | Delay | Pending | Done
|  | Assignment: | Thien Pham | Duy Tran | Khoi Nguyen | All members | RVC
2. Risks
| No. | Risks | Description | Scope | Action Description | Status
3. Progress
| No. | Tasks | Start date | End date | Assignment | Progress(%) | Status | Issue/Q&A | Cause/Solution | Remark
| 1 | Update introduction document (slides) for CanEthConv | 2023-06-12 | 2023-06-16 | Thien Pham | 100 | Done |  |  | 2 days only as I took sick-leave 2 days this week.
| 2 | Study performance testing with CanEthConv | 2023-06-12 | 2023-06-16 | Thien Pham | 10% | Normal |  |  | Seems not enough information but would like to init when we have more information
| 3 | Running Sample app for CAN Routing module | 2023-05-15 | 2023-06-06 | Khoi Nguyen | 60 | Normal |  |  | Use CANoe instead of PCAN
| 4 | Maintain CanRouting introduction slides | 2023-06-06 | 2023-06-16 | Khoi Nguyen | 100 | Done
| 5 | Research and Know How to execuse Integration Test. | 2023-06-07 | 2023-06-12 | Duy Tran | 100 | Done
| 6 | Finding Fix Ethernet Switch Control Introduction slides | 2023-06-13 | 2023-06-15 | Duy Tran | 100 | Done
4. Next plan:
| No. | Action Items | Assignment | Remark
| 1 | Study Gen5 design documents, study some related tools for Gen5 development (VDK, Quemu, ..) | Thien Pham | Seems not enough information but would like to init when we have more information
| 2 | Study Gen5 design documents, study some related tools for Gen5 development (VDK, Quemu, ..) | Duy Tran
| 3 | Update CAN_Rout Sample App Guideline | Khoi Nguyen
4