## Revision
Revision History
Version | Date | Revision Content | Created by
W1 | 2023-05-12 | Weekly report for W1 (8-May -> 12-May) | Duy Tran
W2
W3
W4

## W1
1. Information
|  | Duration: | From | 2023-05-08 | To | 2023-05-12
|  | Status: | Open | Normal | Delay | Pending | Done
|  | Assignment: | Thien Pham | Duy Tran | Khoi Nguyen | All members | RVC
2. Risks
| No. | Risks | Description | Scope | Action Description | Status
3. Progress
| No. | Tasks | Start date | End date | Assignment | Progress(%) | Status | Issue/Q&A | Cause/Solution | Remark
| 1 | Understanding S4, update sharing document for CAN_ETH_conversion module. Need a clear list of QnA. | 2023-04-20 | 2023-05-19 | Thien Pham | N/A | Normal
| 2 | Translate 4 files | 2023-04-27 | 2023-05-12 | Thien Pham | 100 | Done
| 3 | Running Sample app for CAN_ETH_conversion module | 2023-05-05 | 2023-05-16 | Thien Pham | 10 | Normal
| 4 | Understanding S4, update sharing document for CAN Routing module. Need a clear list of QnA. | 2023-04-20 | 2023-05-19 | Khoi Nguyen | N/A | Normal
| 5 | Translate 4 files | 2023-04-27 | 2023-05-12 | Khoi Nguyen | 100 | Done
| 6 | Running Sample app for CAN Routing module | 2023-05-05 | 2023-05-16 | Khoi Nguyen | 10 | Normal
| 7 | Understanding S4, update sharing document for EthernetSwitchControl module. Need a clear list of QnA. | 2023-04-20 | 2023-05-19 | Duy Tran | N/A | Normal
| 8 | Translate 4 files | 2023-04-27 | 2023-05-12 | Duy Tran | 100 | Done
| 9 | Running Sample app for EthernetSwitchControl module | 2023-05-05 | 2023-05-16 | Duy Tran | 50 | Normal
4. Next plan:
| No. | Action Items | Assignment
| 1 | Run SampleApp for Gateway (Task 2) and create a guideline | All members
2
3
4