## Sheet1
1. Information
|  | Duration: | From | 2023-05-22 | To | 2023-05-26
|  | Status: | Open | Normal | Delay | Pending | Done
|  | Assignment: | Thien Pham | Duy Tran | Khoi Nguyen | All members | RVC
2. Risks
| No. | Risks | Description | Scope | Action Description | Status
3. Progress
| No. | Tasks | Start date | End date | Assignment | Progress(%) | Status | Issue/Q&A | Cause/Solution | Remark
| 1 | Exceution of SampleApp Testcases (53/53 CanEthConv and 67/67 CanEthConv PackLib) | 2023-05-18 | 2023-05-19 | Thien Pham | 85 | Normal |  |  | - All basic tests done, test reported done. - For performance test we don't know how to execute - Already report the case to Toan Pham, wait feedback so that we can continue work on performance testing.
| 2 | Update sharing document regarding to how-to run SampleApp for CanEthConv | 2023-05-22 | 2023-05-26 | Thien Pham | 100 | Done
| 3 | DUT for - R_CanEthConv_Init - CreateEthHeaderIpv4Ntscf | 2023-05-22 | 2023-05-26 | Thien Pham | 20 | Normal |  |  | - Understand the TableDriven workflow - Need more time to study the details - Created first 4 testcases
| 4 | Running Sample app for CAN Routing module | 2023-05-15 | 2023-05-19 | Khoi Nguyen | 50 | Pending
| 5 | Refer SIVI project for testing sample app by CANoe | 2023-05-22 | 2023-05-26 | Khoi Nguyen | 60 | Normal
| 6 | Execute Sample App (6/7 Test Cases) of Ethernet Switch Control Module and Get Test Log, Make Test Report. | 2023-05-22 | 2023-05-23 | Duy Tran | 95 | Done |  |  | Can mark as Done because 1 Test Case needs Linux PC to boot CA55 core.
| 7 | Investigate DUT (Driver Unit Test) process: - Set up Cantata environment. - How to make Test Specification & create Test Application. - How to run Test Application in QAsystem Cantata. - Execute 2 functions of EthSwtCont module (SetMacTbl, CheckMacTblCfg) | 2023-05-23 | 2023-05-26 | Duy Tran | 25 | Normal
4. Next plan:
| No. | Action Items | Assignment
1
2
3
4