## Sheet1
1. Information
|  | Duration: | From | 2023-05-15 | To | 2023-05-19
|  | Status: | Open | Normal | Delay | Pending | Done
|  | Assignment: | Thien Pham | Duy Tran | Khoi Nguyen | All members | RVC
2. Risks
| No. | Risks | Description | Scope | Action Description | Status
|  | Execution SampleApp for CANrout module | Because of lacks of env: SW: PCAN View HW: PCAN FD => Cause delay for this task. | Khoi Nguyen | Try to execuse with workaround solution
3. Progress
| No. | Tasks | Start date | End date | Assignment | Progress(%) | Status | Issue/Q&A | Cause/Solution | Remark
| 1 | Understanding S4, update sharing document for CAN_ETH_conversion module. | 2023-05-18 | 2023-05-19 | Thien Pham | 70 | Normal | Will have a short list of questions.
| 2 | Update sharing document regarding to how-to run SampleApp for CanEthConv | 2023-05-15 | 2023-05-19 | Thien Pham | 100 | Done
| 3 | Running Sample app for CAN_ETH_conversion module | 2023-05-15 | 2023-05-19 | Thien Pham | 100 | Done
| 4 | Translate R-CarS4_Gateway_SampleProgramTestReport_CanEthConv.xlsx | 2023-05-18 | 2023-05-23 | Thien Pham | 0 | Open
| 5 | Update the Introduction Slides (for Can Routing Module) | 2023-05-15 | 2023-05-19 | Khoi Nguyen | 100 | Done
| 6 | Running Sample app for CAN Routing module | 2023-05-15 | 2023-05-19 | Khoi Nguyen | 50 | Pending | Need HW & SW to run sample app: SW: PCAN driver (PCAN -view, PCANBasic API) HW: PCAN-USB x6, PCAN-USB Pro FD | Try to execuse with workaround solution
| 7 | Translate R-CarS4_Gateway_SampleProgramTestReport_CanRout.xlsx | 2023-05-17 | 2023-05-17 | Khoi Nguyen | 100 | Done
| 8 | Execuse Sample Application for Ethernet Switch Control Module: - Hardware set-up. - Execuse all Test Cases. - Make the Sample App Guideline. | 2023-05-05 | 2023-05-16 | Duy Tran | 100 | Done
| 9 | Update the Introduction Slides (for Ethernet Switch Control Module) | 2023-05-15 | 2023-05-19 | Duy Tran | 100 | Done
| 10 | Translate R-CarS4_Gateway_SampleProgramTestReport_EthSwtCont.xlsx | 2023-05-17 | 2023-05-17 | Duy Tran | 100 | Done
4. Next plan:
| No. | Action Items | Assignment
1
2
3
4