## Sheet1
1. Information
|  | Duration: | From | 2023-05-29 | To | 2023-06-02
|  | Status: | Open | Normal | Delay | Pending | Done
|  | Assignment: | Thien Pham | Duy Tran | Khoi Nguyen | All members | RVC
2. Risks
| No. | Risks | Description | Scope | Action Description | Status
3. Progress
| No. | Tasks | Start date | End date | Assignment | Progress(%) | Status | Issue/Q&A | Cause/Solution | Remark
| 1 | DUT for - Function 1 - R_CanEthConv_Init - Setup Environment - Study Table Driven Script - Study Cantata Environment - Generate Test App - Execute 12 testcases, expect all PASSED | 2023-05-29 | 2023-06-02 | Thien Pham | 100 | Done |  |  | ETA: 4MD in the trial phase.
| 2 | DUT for - Function 2 - CreateEthHeaderIpv4Ntscf - Study Table Driven Script - Generate Test App - Execute TBD testcases, expect all PASSED | 2023-06-05 | 2023-06-09 | Thien Pham | 0 | Open |  |  | Seems a complecated function
| 3 | Running Sample app for CAN Routing module | 2023-05-15 | 2023-06-01 | Khoi Nguyen | 50 | Pending
| 4 | Catch message from board to CANoe based on RCAR_S4_SPRINT14_CAN_DEVELOP project | 31/5/2023 | 2023-06-01 | Khoi Nguyen | 30 | Normal |  |  | Detected: . CANoe can send . CAN/LIN board has tranceiver .
| 5 | Refer SIVI project for testing sample app by CANoe | 2023-05-22 | 2023-06-01 | Khoi Nguyen | 80 | Normal
| 6 | Investigate DUT (Driver Unit Test) process: - Set up Cantata environment. - How to make Test Specification & create Test Application. - How to run Test Application in QAsystem Cantata. - Execute 2 functions of EthSwtCont module (SetMacTbl, CheckMacTblCfg) (Request by REL) - Make test report | 2023-05-29 | 2023-05-31 | Duy Tran | 100 | Done
| 7 | Self-investigate DUT for complex function (SetL2L3UpRuleTbl) | 2023-06-01 | 2023-06-02 | Duy Tran | 100 | Done
4. Next plan:
| No. | Action Items | Assignment
1
2
3
4